FEASIBILITY STUDY REPORT

# IntelliMeet Pro: AI Meeting Assistant & Workflow Management

Mustafa Masood 22k-4818

Laiba Fatima 22k-5195

Sabina Rasheed 22k-5198

## 1.0	GENERAL INFORMATION

## 1.1		Purpose

  - This feasibility study report is written to ensure that the project plan is feasible. It will evaluate the financial, technical, operational possibility of IntelliMeet Pro, which is an AI Meeting Assistant. It is meant to join virtual meetings and then provide meeting transcription,  generate summary, extract key action items and integrate with project management tools.

## 1.2		Scope

1.2.1 	In Scope

IntelliMeet Pro will make use of AI bots to automatically join Google Meets, Zoom, Microsoft Teams to capture data. It will process and then generate meeting transcriptions and summarries. It will also implement speaker diarization with persistent voice identification. It will provide a semantic search functionality to allow users to query transcripts, which will enable easy retrieval of information. IntelliMeet Pro will integrate with Jira, Trello, Asana and Slack so that extracted tasks are directly aligned with workflows.

1.2.2 	Out Scope

IntelliMeet Pro will not include real-time video processing or computer vision features.

It is not being developed as a Mobile application (iOS/Android). IntelliMeet Pro will not have integration features to customer relationship management (CRM) systems or human resources management (HRM) systems. It will not handle advanced AI training and AI model fine tuning. It will also not include text-to-speech features. IntelliMeet Pro will not be able to provide end-to-end encryption for stored data.

## 1.3		Project Overview

IntelliMeet Pro is an AI meeting assistant which will join virtual meetings. It will automatically transcribe and summarize meetings, extract action items, and integrate with collaboration tools such as Slack, Jira, and Trello. IntelliMeet Pro is going to provide persistent speaker identification across multiple sessions, and semantic search which will make quick retrieval of information possible.

| Process Owner | : FAST |
| --- | --- |
| Proposed Project Name | : IntelliMeet Pro |
| Proposed Project Abbreviation | : IMP |

## 1.4	Project References

- https://asana.com/resources/feasibility-study

- https://www.investopedia.com/terms/f/feasibility-study.asp

- https://www.indeed.com/career-advice/career-development/feasibility-report

## 2.0	MANAGEMENT SUMMARY

### 2.1	Environment

#### 2.1.1	Organizations Involved

Project Information

| Process Owner | FAST |
| --- | --- |
| Project Owner | Mustafa, Laiba |
| Project Type | Mixed mode |

Project Sponsor/ Director

| No. | Name | Roles |
| --- | --- | --- |
| 1. | Syeda Rubab | Supervisor |
| 2. | Minhal Raza | Teacher |

Functional Team Members

| No. | Name | Roles |
| --- | --- | --- |
| 1. | Mustafa Masood | Functional Project Manager |
| 2. | Laiba Fatima | Functional Team Member |

Proposed Technical Team Members

| No. | Name | Roles |
| --- | --- | --- |
| 1. | Mustafa Masood | Technical Project Manager |
| 2. | Laiba Fatima | Technical Team Member |

#### 2.1.2	Input/output

IntelliMeet Pro will process audio meetings that contain meeting data and data from the calendar as inputs. It will then generate outputs in the form of meeting transcript, summary and action items.

#### 2.1.3	Processing

IntelliMeet Pro will implement speech-to-text through Whisper API. Transformer-based LLMs will  handle summarization of meetings and extraction of action items. Semantic Search across previous meeting records will be made possible by retrieval-augmented generation (RAG) pipeline.

#### 2.1.4	Security

IntelliMeet Pro will provide different level permissions for Admin, Team lead and members by implementing role based access control. With the usage of Stripe, secure payment channels will handle all transactions with webhook validation preventing	 fraud.

#### 2.1.5	System Interaction

The platform will be designed to integrate with popular video conferencing tools such as Zoom, Microsoft Teams, and Google Meet. Moreover, it will connect with project management tools including Jira, Trello, and Asana to log action items. A Slack bot for conversational access for meeting insights, enabling teams to query transcripts, summaries, and tasks directly within their workspace.

#### 2.1.6	Physical Environment

| System environment or special conditions needed |  |
| --- | --- |
| Estimated Number of Users | : 50–100 |
| Internet or Intranet or both Usage | : Internet (web-based, accessible via browser) |
| Required storage? (require documents/files to be stored (upload feature) ?) | : Encrypted storage for transcripts, summaries, and uploaded meeting files. |
| Database | : PostgreSQL + Pinecone vector DB |
| Application Server | : Azure App Services |
| Special features? (Please describe) | : API integrations with video conferencing tools, project management platforms, and Slack; bilingual transcription/summarization; action extraction. |
| Others? (Please state) | : Browser compatibility |

### 2.2	Current Functional Procedures

Currently, Otter.ai serves as a popular automated transcription service that processes audio and video meeting streams to generate text transcripts. The major processing flow involves capturing live audio from conferencing platforms such as Zoom, Teams, or Google Meet, applying speech-to-text algorithms, and delivering transcripts in near real time. The system is primarily cloud-based, requiring no specialized hardware apart from standard laptops or mobile devices connected to the internet. Otter.ai supports a high volume of meetings per user, with scalability handled through its subscription-based cloud infrastructure.

Costs are incurred through tiered subscription plans, ranging from free basic access to enterprise-level packages with advanced features. The service requires minimal staff effort to operate, as end users simply join meetings or upload recordings, and transcripts are generated automatically. No dedicated technical expertise is needed from users beyond basic application usage. However, Otter.ai primarily focuses on transcription and note-taking, with limited integration for structured action extraction, persistent speaker diarization across sessions, and enterprise project management workflows. These limitations highlight the gap between current functional procedures and the objectives of IntelliMeet Pro.

### 2.3	Functional Objectives

IntelliMeet Pro aims to automate manual processes and significantly increase efficiency while reducing the likelihood of errors. It will introduce centralized data management through PostgreSQL and Pinecone DB, enabling streamlined document upload, storage, and retrieval. The solution will provide real-time online access through internet connectivity, ensuring flexibility for users. Privacy, security, and role-based access controls will be embedded into the system to meet compliance and audit requirements. The system will also feature on-demand report generation and analytics to improve decision-making. Furthermore, the platform is designed to be scalable, supporting between 50–100 concurrent users without performance issues. The target completion date for implementation is estimated within six to eight months.

### 2.4	Assumptions and Constraints

    - 2.4.1 Personnel

          - Assumptions

- The two student developers will remain consistently available and committed throughout the project timeline.

- The student team has or will acquire the required skills in AI integration, backend development, cloud storage, and API usage (OpenAI, Zoom, Google Meet, Azure).

- University supervisors and advisors will be available for regular feedback and support during key milestones.

- External technical consultation or mentoring (AI or system integration) will be available on time via university resources.

Constraints

- Only two team members are available, limiting parallel task execution.

- No access to professional developers or a QA team, restricting testing depth.

- No dedicated UI/UX designers or DevOps engineers, limiting design polish and deployment automation.

        - 2.4.2 Timing

Assumptions

- The academic schedule will remain stable without major disruptions.

- Development will progress steadily alongside academic responsibilities.

- Milestones (mid-term submissions, demos, supervisor reviews) will be met and used as checkpoints.

Constraints

- Final project must be delivered by May 2026, aligned with FYP deadlines.

- Any delays in APIs, debugging, or integrations may risk timely completion.

- Limited time for performance optimization, user testing, and documentation.

            - 2.4.3 Budget

Assumptions

- The project will use free-tier services, student licenses, open-source tools, and personal computing resources.

- Services like OpenAI, Azure Blob Storage, Pinecone, and integrations (Zoom, Slack, Jira) will be accessible through free tiers or student credits.

- No significant personal expenses for hardware, software, or infrastructure are expected.

Constraints

- No formal budget has been allocated, restricting use of premium services.

- All technology decisions must be cost-efficient and within free usage limits.

- The project cannot outsource development or purchase commercial-grade tools for UI/UX, testing, or monitoring.

2.5	Risk

| Risk Register |  |  |  |  |
| --- | --- | --- | --- | --- |
| Type of Risk | Risk Description | Mitigation Plan | Risk owner | Risk Timeline |
| Human Resource | Absence due to workload | Task redistribution | Functional PM | 2 weeks |
|  | Lack of expertise | Upskilling | Tech Lead | 2-3 weeks |
| Business Process | Misaligned expectations | Regular demo | PM | Monthly |
|  | Scope creep | Freeze scope mid-project | PM | development |
| Financial | API free-tier limits | Student credits/alternatives | Project Member | development |
|  | Cloud cost issues | Use free/university license | Project Member | deployment |
| Infrastructure/ Applications / Database | Cloud downtime | Local backups | Project member | testing |
|  | Large audio slowdown | File limits | Tech lead | testing |
| Third Party Supplier & Outsourcing | API changes | Backup APIs | Tech lead | integration |
|  | Integration failures with external tools | fallback manual import/export | Project member | integration |

### 2.6	Methodology

The methodology was designed to systematically evaluate the feasibility of IntelliMeet Pro by combining qualitative and quantitative approaches. The primary objective was to ensure that the proposed AI-powered meeting assistant and workflow management system could be practically implemented, economically viable, and aligned with user needs. A mix of market research, stakeholder input, financial analysis, and technical prototyping was employed to establish a comprehensive evidence base for decision-making.

### Methods Employed

1. Surveys and Questionnaires

- A structured survey was distributed to potential end users, including students, faculty, and small business teams.

- The survey gathered insights on current pain points in meeting management, preferred integrations (Zoom, Teams, Slack), and willingness to adopt an AI-driven solution.

- Responses provided a clear understanding of functional priorities such as transcription accuracy, action item extraction, and project management integration.

2. Benchmarking Against Industry Practices

- Existing platforms such as Otter.ai and Fireflies.ai were benchmarked to assess their strengths and limitations.

- Comparative analysis highlighted gaps in persistent speaker diarization, semantic search, and enterprise integrations  validating IntelliMeet Pro’s differentiated value proposition.

- Pricing models of competitors were also studied to inform subscription strategy.

3. Decision Matrix (Weighting Model)

- A weighted scoring model was developed to evaluate potential system features against feasibility criteria such as technical complexity, user demand, cost, and scalability.

- Features like transcription accuracy and project management integration received higher weights based on survey findings, guiding prioritization for development.

4. Financial Modeling

- Basic financial models were constructed using Excel to estimate costs and returns.

- Metrics such as Return on Investment (ROI), Net Present Value (NPV), and Payback Period were calculated based on projected subscription revenues.

- This analysis demonstrated the economic viability of the SaaS model, particularly under a three-tier subscription plan.

5. Prototyping and Simulation

- A small-scale prototype was built using OpenAI Whisper API for transcription and Pinecone for semantic search.

- This prototype validated the technical feasibility of integrating diarization and semantic search in real time.

- Simulation of integration with Jira and Trello APIs was performed to confirm interoperability with external project management systems.

2.7	Statement of Needs (Business Case)

2.7.1	Benefits and impact to the University

The proposed system will enhance productivity by automating meeting transcription, summarization, and action item extraction, allowing users to focus on strategic work rather than manual note-taking. It will improve collaboration across departments by providing centralized, searchable meeting records and seamless integration with project management platforms. The system will also serve as a research asset, showcasing the university’s capability in AI, natural language processing, and workflow automation, strengthening its reputation for innovation and digital transformation.

2.7.2	Please indicate the value added of the project to the University

The project will provide significant value by reducing time and effort spent on meeting documentation, thus lowering operational overhead. As a student-led innovation, it will also highlight the university’s role in nurturing practical AI-driven solutions, which may attract partnerships, funding, and recognition in academic and industry forums. In the long term, the system could be scaled for broader adoption within the institution, representing a high return on investment in terms of efficiency, knowledge management, and academic visibility.

## 3.0	AUTOMATION INITIATIVES

### 3.1	Time and Resource Costs Required

For the IntelliMeet Pro project, the estimated effort across the full system lifecycle spanned approximately 280 person-days within the available 242 calendar days (Sept 2025 - May 2026). With two student developers contributing at a 70–75% effective availability (to account for academic workload, exams, meetings, and unavoidable absences), this level of effort remained feasible and realistic.

Resource allocation was phased to match the incremental development model and university evaluation calendar: requirements gathering and literature review consumed around 20 person-days, system design and architecture 30 person-days, and three development increments (covering authentication, meeting scheduling, transcription, summarization, workflow integration, and multilingual support) accounted for the largest share at 120 person-days. Testing, spread across increments, required 40 person-days, while deployment and CI/CD setup accounted for 10 person-days.

A further 10 person-days were dedicated to training, demo preparation, and user guidelines, 20 person-days to evaluation and limited operations/maintenance during the review period, and 5 person-days to retirement planning and final report write-up. These estimates incorporated procurement lead time in October 2025, allowances for semester breaks and Eid/public holidays, and a 10–15% contingency buffer to absorb delays or rework. Since this was a university Final Year Project, no staff salaries were cost, and financial requirements were minimal, restricted to small out-of-pocket expenses for documentation, presentation materials, and potential API usage beyond free student credits.

3.1.1	Project Timeline

The IntelliMeet Pro project followed a 9-month academic calendar (Sept 2025 - May 2026, ~242 days), with tasks distributed to balance development effort, evaluations, semester breaks, procurement lead times, and final installation. The schedule below reflects realistic student workload and institutional checkpoints.

| No. | Task Name | Proposed Date |
| --- | --- | --- |
| 1. | FYP Registration & Proposal Submission | Aug – Early Sept 2025 |
| 2. | Proposal Defense Presentation | Mid Sept 2025 |
| 3. | Initial Requirements Gathering & Stakeholder Discussions | Mid–Late Sept 2025 |
| 4. | Literature Review & Drafting of SRS | Late Sept – Early Oct 2025 |
| 5. | System Architecture Design | Early Oct 2025 |
| 6. | Database Schema & ERD Development | Early–Mid Oct 2025 |
| 7. | UI Wireframing & Prototyping | Mid Oct 2025 |
| 8. | Procurement of Tools, APIs, and Student Licenses | Mid–Late Oct 2025 |
| 9. | Increment 1 Development – Authentication & Meeting Scheduling | Early–Mid Nov 2025 |
| 10. | Increment 1 Testing, Debugging & Refinement | Mid–Late Nov 2025 |
| 11. | Proposal Final Defense + Evaluation + Literature Review/SRS/SDS Submission | Late Nov 2025 |
| 12. | Increment 2 Development – AI Transcription & Speaker Diarization | Dec 2025 |
| 13. | Increment 2 Development – Meeting Summarization & Action Item Extraction | Dec 2025 – Early Jan 2026 |
| 14. | Semester Break & Public Holidays Buffer (Winter + Jan Break) | Late Dec – Early Jan 2026 |
| 15. | Increment 2 Testing & Refinement | Jan 2026 |
| 16. | Mid Evaluation & Progress Report Submission | Mid Jan 2026 |
| 17. | Increment 3 Development – Semantic Search & Workflow Integration (Jira, Trello, Asana) | Late Jan – Feb 2026 |
| 18. | Increment 3 Development – Slack Bot Conversational Assistant | Feb 2026 |
| 19. | Increment 3 Testing & QA | Late Feb – Early Mar 2026 |
| 20. | User Training Sessions & Demo Preparation | Mid Mar 2026 |
| 21. | Eid-ul-Fitr Holidays (Buffer) | Mar 19–20, 2026 |
| 22. | Increment 4 Development – UI/UX Enhancements & Multilingual Support | Mid–Late Mar 2026 |
| 23. | Increment 4 Development – Payment System & Notifications | Mar – Early Apr 2026 |
| 24. | Final Integration & System-Wide Testing | Apr 2026 |
| 25. | Documentation (Design Docs, Test Reports, User Manual) | Apr 2026 |
| 26. | Final Deployment & Cloud Installation | Late Apr – Early May 2026 |
| 27. | Final Presentation Preparation & Open House Demo | May 2026 |
| 28. | Final Evaluation, Viva & Retirement Planning Report | May 2026 |
| Total Months Needed: |  | 9 months |

3.1.2	Project Cost

Since this is a Final Year Project, the direct financial cost is minimal. The main costs come from software tools, cloud credits, and API usage. All development work is carried out by students as part of coursework.

| Source of Budget |  | : |  |
| --- | --- | --- | --- |
| Bil | Items |  | Budget Allocated |
|  | OpenAI / NLP APIs (free tier + trial credits) |  | 10,000 |
|  | Documentation & Presentation (printing, binding, demo setup) |  | 5,000 |
|  | Contingency (miscellaneous small expenses) |  | 5,000 |
| GRAND TOTAL |  |  | PKR 20,000 |

3.2	Existence of Similar Initiatives or System

While existing platforms such as Otter.ai, Fireflies.ai, and Avoma provide transcription and summarization services, they do not fully address the needs of the university environment. These tools are either cost-prohibitive, lack persistent diarization, or have limited integration with project management platforms. IntelliMeet Pro fills this gap by offering a secure, cost-efficient, and customizable solution tailored to academic and collaborative project requirements.

### 3.3	Impacts

#### 3.3.1	Equipment Impacts

No specialized hardware is required beyond standard student laptops and servers provided through cloud hosting on Microsoft Azure. Existing computing resources are sufficient, with minor adjustments for cloud storage and processing requirements.

#### 3.3.2	Software Impacts

The system introduces new software modules, including Whisper API for transcription,  transformer-based LLMs for summarization, and Pinecone for semantic search. Integration with conferencing platforms (Zoom, Google Meet, Teams) and project management tools (Jira, Trello, Slack) will require minimal configuration but no replacement of existing university systems.

#### 3.3.3	Organizational Impacts

The system will require users to adapt to automated workflows, such as receiving transcripts and action items instead of manual note-taking. No major restructuring of organizational roles is necessary, though basic training will be required to familiarize users with system capabilities.

#### 3.3.4	Operational Impacts

Operational procedures will shift toward automation. User operating procedures will focus on initiating the AI assistant during meetings and retrieving summaries and action items after. Data entry and note-taking will be replaced by transcripts. Retrieval procedures will improve through semantic search capabilities. Reporting will be automated with structured summaries and project management updates.

#### 3.3.5	Developmental Impacts

Development will require integration testing with conferencing APIs and project management tools. Resources will be allocated for building the database using PostgreSQL and Pinecone. Processing resources will rely on Azure cloud services for scalability. Privacy and security implications will be addressed through encrypted storage, role-based access control, and compliance with secure webhook validation.

#### 3.3.6	Site or Facility Impacts

No physical site or facility modifications are needed, as the solution is cloud-based and delivered as a SaaS platform. Users will access the system via a web application, requiring only internet connectivity.

#### 3.3.7	Security and Privacy Impacts

The system must enforce strict security controls due to the sensitive nature of meeting content. Encrypted transcript and audio storage, secure payment integration via Stripe, and role-based access control will safeguard user data. Privacy will be prioritized to avoid intrusive bot behavior and unauthorized access, differentiating IntelliMeet Pro from competing systems.

### 3.4	Rationale for Recommendations

The proposed IntelliMeet Pro system is recommended over existing alternatives because it directly addresses the shortcomings of current solutions. Unlike Otter.ai or Fireflies.ai, IntelliMeet Pro provides persistent diarization, robust semantic search, and deep integration with project management platforms. The design prioritizes privacy, security, and cost-effectiveness, making it suitable for use where budgets are limited. Its scalability and bilingual support further enhance inclusivity and global collaboration. This makes IntelliMeet Pro not only a competitive solution but also the most practical and sustainable choice for adoption.