FAST Tech Solutions has initiated Project Zenith, a 10-month project to develop a Smart Campus Automation System (SCAS) for a major university. The system will automate attendance tracking, classroom energy management, and security monitoring using IoT sensors and AI-driven analytics.

The project involves five distributed teams working across Lahore, Islamabad, and Karachi. The software team in Lahore is responsible for the AI algorithms, while the hardware integration is managed in Karachi. The data security and cloud infrastructure team in Islamabad must ensure compliance with strict government data privacy regulations.

During the requirements phase, the client requested a last-minute integration with an unapproved third-party biometric vendor to reduce costs. The vendor’s API documentation is incomplete and available only in another language. The procurement officer has not yet verified the vendor’s compliance status.

Meanwhile, the project manager has noticed that half of the IoT devices shipped from China are delayed due to custom clearance issues. The hardware team is now using old prototype boards for initial testing, which have known voltage stability problems.

The AI team lead has recently resigned, and the new hire has limited experience with Python-based AI frameworks used in this project. Additionally, one of the key clients insists on frequent weekly demonstrations, despite the teams being in different time zones and already struggling with video call connectivity and power outages.

The university’s semester start date has been moved one month earlier, meaning the project delivery must now happen two weeks before the original deadline. No extra resources have been approved.

| # | Hidden Risk | Description |
| --- | --- | --- |
| R1 | Third-party biometric vendor non-compliance | Unverified vendor may not meet security/privacy laws → project may face legal or technical rework. |
| R2 | Incomplete vendor API documentation | API issues may delay integration and cause software-hardware incompatibility. |
| R3 | IoT hardware shipment delay | Customs clearance issues cause late delivery, delaying installation and testing. |
| R4 | Prototype hardware instability | Using old boards may cause voltage failures or data inaccuracies in early testing. |
| R5 | AI team lead resignation | Skill gap may cause slower progress and incorrect AI model implementation. |
| R6 | Time zone, power, and communication issues | Remote teams face sync delays, causing coordination and reporting issues. |
| R7 | Deadline shortened by 2 weeks | Schedule compression increases workload and reduces quality time for testing. |
| R8 | Lack of resource approval | No additional resources despite earlier delivery timeline increases burnout risk. |

| Risk ID | Risk Description | Risk Type | Likelihood / Probability | Severity / Impact | Priority | Mitigation / Preventive Action |
| --- | --- | --- | --- | --- | --- | --- |
| R1 | Third-party biometric vendor may fail compliance check | External / Regulatory | High | High | Critical (P1) | Conduct immediate compliance audit; select alternate vendor if needed |
| R2 | Incomplete API documentation delays integration | Technical | High | Medium | High (P2) | Assign technical liaison for translation; build mock interface for early testing |
| R3 | IoT device shipment delays | External / Supply Chain | Medium | High | High (P3) | Follow up with customs; consider local backup suppliers |
| R4 | Prototype boards have voltage instability | Operational / Technical | Medium | Medium | Medium (P4) | Limit usage to software testing only; order stable testing kits |
| R5 | AI team lead resignation and skill gap | Human Resource / Organizational | High | High | Critical (P1) | Assign mentor from another project; provide rapid AI framework training |
| R6 | Poor communication due to time zones and outages | Managerial / Coordination | Medium | Medium | Medium (P4) | Use asynchronous tools (e.g., Slack, Trello); set clear documentation protocols |
| R7 | Deadline shortened without extra resources | Schedule / Management | High | High | Critical (P1) | Re-prioritize deliverables; negotiate phased delivery plan |
| R8 | No additional resources approved | Resource / Financial | Medium | High | High (P2) | Prepare cost-justified change request; redistribute existing staff |

| Impact ↓ / Likelihood → | Low | Medium | High |
| --- | --- | --- | --- |
| High Impact | — | R3, R8 | R1, R5, R7 |
| Medium Impact | — | R4, R6 | R2 |
| Low Impact | — | — | — |

Critical (Red Zone): R1, R5, R7

High (Orange Zone): R2, R3, R8

Medium (Yellow Zone): R4, R6

Numerical Scenario: Project Zenith — Smart Campus Automation System

FAST Tech Solutions has initiated Project Zenith, a 10-month project worth PKR 50 million to develop a Smart Campus Automation System (SCAS) for a university.

The project aims to automate attendance tracking, classroom energy control, and campus surveillance using AI + IoT. The project involves three city teams (Lahore, Islamabad, Karachi) with the following key details:

| Parameter | Value |
| --- | --- |
| Project Duration | 10 months |
| Total Budget | PKR 50,000,000 |
| Expected Profit Margin | 18% |
| Deadline Compression | 2 weeks earlier than planned |
| Team Distribution | Lahore (Software), Karachi (Hardware), Islamabad (Cloud/Security) |
| Current Completion Progress | 25% |
| Contingency Reserve | PKR 2,000,000 |

In the Project Zenith case, several quantifiable risks threaten both the budget and schedule. The integration of a third-party biometric vendor, offered at a cost of PKR 3.5 million (20 percent cheaper than approved suppliers), carries a non-compliance risk that could lead to a PKR 6 million penalty, with a 0.4 probability of occurrence. Incomplete API documentation may result in a two-week rework for the software team, costing PKR 800,000 per week and having a 0.6 likelihood. The delay of half of the 1,000 IoT sensors in customs could cause a one-month setback and an additional PKR 2 million in logistics expenses, with a 0.5 probability. Using outdated prototype boards introduces instability risks that may require PKR 1.2 million in replacements and retesting, with a 0.3 probability. The resignation of the AI team lead could reduce productivity for a month, potentially causing PKR 3.8 million in rework costs and carrying a 0.7 probability. Communication barriers across teams in different time zones may lead to a two-week coordination delay, adding PKR 500,000 per week in duplicated work, with a 0.5 probability. The newly shortened project deadline by two weeks will likely increase operational costs by PKR 1.5 million and quality-related losses by PKR 2 million (a combined impact of PKR 3.5 million) at a 0.8 probability. Finally, the lack of additional staff may extend the testing phase by one month, leading to PKR 2.5 million in overhead losses, with a 0.6 likelihood.

| Risk ID | Description | Probability | Impact (PKR) | Risk Exposure (P × I) | Risk Type | Priority |
| --- | --- | --- | --- | --- | --- | --- |
| R1 | Vendor non-compliance penalty | 0.4 | 6,000,000 | 2,400,000 | External / Regulatory | High |
| R2 | API delay and rework | 0.6 | 1,600,000 | 960,000 | Technical | Medium |
| R3 | Customs delay for IoT sensors | 0.5 | 2,000,000 | 1,000,000 | External / Supply Chain | High |
| R4 | Prototype hardware instability | 0.3 | 1,200,000 | 360,000 | Operational / Technical | Low |
| R5 | AI team lead replacement cost | 0.7 | 3,800,000 | 2,660,000 | Human Resource | Critical |
| R6 | Coordination / communication failures | 0.5 | 1,000,000 | 500,000 | Managerial / Coordination | Medium |
| R7 | Schedule compression (2 weeks) | 0.8 | 3,500,000 | 2,800,000 | Schedule / Management | Critical |
| R8 | No new resources (testing delay) | 0.6 | 2,500,000 | 1,500,000 | Resource / Financial | High |

Total Expected Monetary Value (EMV)

So, Project Zenith’s total quantified risk exposure = PKR 12.18 million, which equals ~24% of total budget — indicating high overall project risk.

| Impact ↓ / Probability → | Low (<0.3) | Medium (0.4–0.6) | High (>0.6) |
| --- | --- | --- | --- |
| High (>3M PKR) | — | R1, R7 | R5 |
| Medium (1–3M PKR) | — | R2, R3, R8 | — |
| Low (<1M PKR) | R4 | R6 | — |

| Risk | Mitigation Strategy | Cost of Mitigation (PKR) |
| --- | --- | --- |
| R1 | Compliance audit & alternate vendor search | 0.4M |
| R2 | Hire bilingual consultant to translate API docs | 0.3M |
| R3 | Use local IoT vendor as contingency | 0.5M |
| R4 | Restrict prototypes to software simulation | 0.2M |
| R5 | Assign mentor & arrange crash training | 0.6M |
| R6 | Invest in better communication tools | 0.25M |
| R7 | Negotiate milestone-based partial delivery | 0.4M |
| R8 | Contract temporary QA engineers | 0.7M |
|  | Total | 3.35M |

On the basis of Risk Matrix

| Risk | EMV (PKR) | Level |
| --- | --- | --- |
| R7 – Schedule compression | 2.8M | Critical |
| R5 – AI team lead resignation | 2.66M | Critical |
| R1 – Vendor non-compliance | 2.4M | High |

Highest exposure: R7 (Schedule compression) and R5 (AI team loss)

Top mitigation priority: Focus on R1, R5, R7 to cut down ~65% of total project exposure

Residual exposure (after mitigation):

Estimated ≈ PKR 12.18M − 3.35M = 8.83M